## Blad1
Task | Priority | Developer | Estimated duration points
Get familiar with the StarCraft API that we will be using and all the functionality | HIGH | Both | 10
Comment and clean the code that is currently available | MEDIUM | Harm | 4
Read about agent programming and how terminology should be (Percepts and Actions, how many literals) | MEDIUM | Danny | 3
Create a general percept-action structure that we will be using, according to the research | MEDIUM | Both | 6
There is a Starcraft competition, what is needed to join this competition and how can Java and GOAL be sent there. Maybe contact people that are involved in organising this competition. | LOW | Harm | 1